## Sheet1
	Gruppe 12	Spam Detection
	6790872	Niklas von Boguszewski
	7346178	Lars Stelzer

Nr.	Date	Task	Deadline/Milestone
1	11.16.2020	-	-
2	11.23.2020	What kind of spam we want to detect?	Goal definition + dataset
3	11.30.2020
4	12.7.2020	Literaturanalysis	Research
5	12.14.2020
6	12.21.2020	Experimental setup	Experimental phase		1
7	12.28.2020	Run experiments
8	1.4.2021	Evaluation
9	1.11.2021	Writing
10	1.18.2021
11	1.25.2021	Submit your paper draft	Paper Draft
12	2.1.2021	Review another groups paper	Reviews
13	2.8.2021	Make changes on own paper based on another groups review	Re-Writing
14	2.15.2021		Final Submission